## Sheet1
Project timeline | 2020 |  |  | 2021 | [11 empty] | 2022
| O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S
Hire and onboard personnel | bar: 2020 O
Develop statistical inference methods
Develop spatial simulations of bear populations | bar: 2020 O to 2021 F
Solicit partner feedback on simulations
Refine simulations based on partner feedback | bar: 2021 M to 2021 A
Implement statistical inference methods
Test statistical inference methods | bar: 2021 M to 2021 J
Apply to available bear data
Develop user-interface | bar: 2021 J to 2021 O
Solicit partner feedback on user-interface
Refine user-interface | bar: 2021 D to 2022 A
Develop user-interface trainings
Trainings and outreach | bar: 2022 M to 2022 S